## Sheet1
Rumaway Tasks: | Status | Context/Detail | Progress | Person
Plan
Concept
UI
Research:
(Bar) Level Research | done
Prop Research | done
Level:
Level design | done |  | could use iteration
Blockout | playable |  | could use iteration
Populating
Assets:
Tankards |  |  |  | Sam
Stools |  |  |  | Sam
Tables |  |  |  | Sam
Mechanics:
GhostDrink:
Ghost Buff | playable | mechanical benefit of buff | got speed boost, needs other bonus | Luke
Buff Visual | passable | a highlighted icon & camera effect | could use an icon & light refinement | Luke
Booze Pickup | done |  | works. just needs better visual + self delete | luke
AI: |  |  |  | Chaz
Problem |  | (thing to run away from) |  | Chaz
Customers |  | optional |  | Chaz
Asthetic:
Textures |  |  |  | Sam
Materials
gamefeel:
Camera shake
Obscure vision
sounds
Artist Polish